## Sheet1
ACTIVITY LOG
Cooperative Loan App
ACTIVITY | START DATE | TARGET END DATE | STATUS | ASSIGNED TO
UI Design | 06-15-2023 | 06-24-2023 | In progress | Joyce Nicole Gonzales Efren Miguel Pelo Karen Arimuhanan
Front End |  |  | **to follow
Back End |  |  | **to follow
Documentation | 06-20-2023 |  | **to follow | Karen Arimuhanan